## Test Script
Test Step Number | Test Step Action | Test Step Expected Result | Pass/Fail | Tester's Initials | Date
1 | Attach Pay Run id to Pay Calender processing 1st payroll Setup HCM > Product Related > Payroll for North America > Processing Controls> Pay Calendar Table | 11A2014170 and 11A2014220 are attached to 170/11-15-1-2014 and 220/11-15-2014 calendars
2 | Create paysheets for 1st payroll Main Menu > Payroll for North American > Payroll Processing USA > Create and Load Paysheets > Create Paysheets | Paysheets are created for all companies associated with Pay Run ID
3 | Mark Test employees OK to PAY = Yes on Paylines Main Menu > Payroll for North American > Payroll Processing USA > Update Paysheets > By Payline | Test employees OK to PAY = Yes (checked)
4 | Run Preliminary calculation for 1st payroll Main Menu > Payroll for North American > Payroll Processing USA > Produce Payroll > Calculate Payroll | Preliminary Calculation completes to success
5 | Run Calculation for 1st payroll Main Menu > Payroll for North American > Payroll Processing USA > Produce Payroll > Calculate Payroll | Calculation completes to success
6 | Run Final Calculation for 1st payroll Main Menu > Payroll for North American > Payroll Processing USA > Produce Payroll > Calculate Payroll | Final Calculation completes to success
7 | Run Confirm Calculation for 1st payroll Main Menu > Payroll for North American > Payroll Processing USA > Produce Payroll > Confirm Payroll | Confirm Calculation completes to success
8 | Run Staff Months Calculation Main Menu > Payroll for North America > CTC Custom > CTC Processes > Staff Months Calculation | Staff Months Calculation completes Successfully
9 | Review Staff Months Calculation Main Menu > Payroll for North America > CTC Custom > Staff Months Calculation | Employees picked have correct Staff Months assigned to the Earnings code and Pay Period
10 | You have successfully completed processing check adjustments. End of Procedure.

## Datasheet
Test Script ID:
Test Script Name: | Staff Months Calculation
Test Set: | Payroll
Test Scenario: | Process Payroll
Test Case: | Staff Months Calculation
CYCLE 1 DATA SET
Concatenation of Test Conditions | Iteration # | Expected Pass/Fail | Iteration Result (Pass/Fail) | Test Step # where Fail was encountered | Browser | Security Role | Run Control ID | Company | Pay Group | Pay Period End Date
| 1 | Pass |  |  | IE | Payroll Administrator | STAFF | 170 | all | 2014-11-15
| 2 | Pass |  |  | Firefox | Payroll Administrator | STAFF | 220 | all | 2014-11-15
| 3 | Pass |  |  | Safari | Payroll Administrator | STAFF | 170 | all | 2014-11-30
| 4 | Pass |  |  | Chrome | Payroll Administrator | STAFF | 220 | all | 2014-11-30

## Datasheet (2)
Employee ID | Employee Record | Company | Paygroup | Earn Code | Pay Begin Date | Pay End Date | Staff Months
101000006 | 0 | 170 | F17 | REG | 2014-11-01 | 2014-11-15 | 0.45
101000006 | 1 | 170 | F17 | HOL | 2014-11-01 | 2014-11-15 | 0.06
101000006 | 0 | 170 | F17 | REG | 2014-11-16 | 2014-11-30 | 0.4
101000006 | 1 | 170 | F17 | HOL | 2014-11-16 | 2014-11-30 | 0.11
101000006 | 0 | 170 | F17 | REG | 2014-11-01 | 2014-11-30 | 0.4
101000007 | 0 | 170 | M7P | REG | 2014-11-01 | 2014-11-30 | 0.12
101000007 | 1 | 170 | M7P | REG | 2014-11-01 | 2014-11-30 | 0.61
101000007 | 2 | 170 | M7P | REG | 2014-11-01 | 2014-11-30 | 0.03
101005444 | 0 | 220 | E22 | REG | 2014-11-01 | 2014-11-15 | 0.45
101005444 | 0 | 220 | E22 | REG | 2014-11-16 | 2014-11-30 | 0.4
101005605 | 0 | 220 | E22 | REG | 2014-11-01 | 2014-11-15 | 0.45
101005605 | 0 | 220 | E22 | REG | 2014-11-16 | 2014-11-30 | 0.4